## sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 88 | 43 | 31 | 12 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Define project objectives and success criteria | 2025-12-01 | 2025-12-01 | Kompella Avanthi krishna Veni | Design | 3- Completed | 2 | Day 1: 2
US-002 | TID-02 | Design high-level Sparkbased architecture | 2025-12-01 | 2025-12-02 | Jillepalli Harshitha | Design | 3- Completed | 3 | Day 1: 2; Day 2: 2
US-002 | TID-03 | Install Java, Spark, and PySpark dependencies | 2025-12-02 | 2025-12-03 | kaif qureshi | Build | 3- Completed | 4 | Day 2: 2; Day 3: 2
US-003 | TID-04 | Configure SparkSession and validate environment | 2025-12-03 | 2025-12-04 | ,Shruti Singh | Build | 3- Completed | 3 | Day 3: 2
US-003 | TID-05 | Design simulated log schema and fields | 2025-12-05 | 2025-12-05 | ,Divya Sree,Malini | Design | 3- Completed | 4 | Day 4: 2; Day 5: 2
US-003 | TID-06 | Generate sample logs using Faker | 2025-06-12 | Others | Bhojanapalli Manikanta Rohit | Coding | 3- Completed | 3 | Day 4: 1; Day 5: 2
US-003 | TID-07 | Implement raw log ingestion logic in Spark | 8/28/2025 | 2025-08-30 | Gorle Sravani | Coding | 3- Completed | 4 | Day 5: 2
SPRINT 2 BACKLOG
US-004 | TID-08 | Create regex patterns for log field parsing | 8/31/2025 | 2025-09-02 | Naga Santhosh Nikhil | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 2; Day 3: 2
US-004 | TID-09 | Convert parsed logs into structured DataFrames | 2025-03-09 | 2025-09-03 | Jillepalli Harshitha | Coding | 3- Completed | 4 | Day 1: 2
US-005 | TID-10 | Implement real-time vehicle counters | 2025-04-09 | 2025-09-05 | M Sandhiya | Design | 3- Completed | 2 | Day 1: 2; Day 2: 2
US-005 | TID-11 | Implement error classification logic | 2025-06-09 | 2025-09-07 | Gorle Sravani | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 2
US-006 | TID-12 | Write Spark SQL queries for log aggregation | 2025-08-09 | 2025-09-09 | Neeraj Vinod | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 2
US-006 | TID-13 | Optimize aggregation queries for performance | 2025-10-09 | 2025-09-11 | Amulya Thupakula | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US-007 | TID-14 | Implement time-window based error analysis | 2025-12-09 | 2025-09-12 | Jillepalli Harshitha | Coding | 3- Completed | 4 | Day 1: 2
SPRINT 3 BACKLOG
US-008 | TID-015 | Design CSV analytics report structure | 9/13/2025 | 2025-09-14 | ,Divya Sree,Malini | Design | 3- Completed | 2 | Day 1: 2; Day 2: 2
US-009 | TID-16 | Implement CSV export logic in Spark | 9/15/2025 | 2025-09-16 | Neeraj Vinod | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 2
US-009 | TID-17 | Design JSON analytics report schema | 9/17/2025 | 2025-09-17 | Kompella Avanthi krishna Veni | Design | 3- Completed | 2 | Day 1: 2
US-011 | TID-18 | Implement JSON export logic in Spark | 9/18/2025 | 2025-09-19 | GORLE SRAVANI | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US-011 | TID-19 | Define alert thresholds for critical errors | 9/20/2025 | 2025-09-21 | Ponnuru Asritha Sai | Design | 3- Completed | 2 | Day 2: 1; Day 3: 2
US-010 | TID-20 | Implement configurable alert logic | 2025-09-22 | 2025-09-23 | Phanikumar Bathina | Coding | 3- Completed | 4 | Day 3: 2; Day 4: 1
US-012 | TID-21 | Design and implement alert history storage schema | 2025-09-24 | 2025-09-25 | Mattaparthi Luhipriya | Build | 3- Completed | 2 | Day 1: 2; Day 2: 2
SPRINT 4 BACKLOG
US-010 | TID-22 | Design Streamlit dashboard layout | 2025-09-26 | 2025-09-27 | Karri Manikanta Sai | Design | 3-Completed | 3 | Day 1: 2; Day 2: 2
US-010 | TID-23 | Connect Spark outputs to Streamlit UI | 2025-09-28 | 2025-09-28 | Annie Valentina A | Coding | 3- Completed | 4 | Day 1: 2
US-012 | TID-24 | Implement error trend visualizations | 2025-09-29 | 2025-09-30 | Behara Sahithya | Coding | 3- Completed | 4 | Day 1: 2; Day 2: 2
US-012 | TID-25 | Implement top error charts using Plotly | 2025-10-01 | 2025-10-02 | Jillepalli Harshitha | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 2
US-013 | TID-26 | Optimize Spark transformations and caching | 2025-10-03 | 2025-10-04 | Amulya Thupakula | Design | 2- In Progress | 5 | Day 1: 2; Day 2: 2
US-013 | TID-27 | Perform end-to-end testing and validation | 2025-10-05 | 2025-10-06 | Neeraj Vinod | System Test | 2- In Progress | 3 | Day 1: 2; Day 2: 2; Day 3: 2
US-013 | TID-28 | Final documentation and Agile report | 2025-10-07 | 2025-10-07 | GORLE SRAVANI | Build | 2- In Progress | 2 | Day 1: 3

## project backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project initialization — define objectives and architecture | MUST HAVE | Project scope | Kompella Avanthi krishna Veni | Completed
S1 | S1 | US-002 | Setup PySpark environment and SparkSession | MUST HAVE | Java, PySpark | Amulya Thupakula | Completed
S1 | S1 | US-003 | Generate simulated server/application log datasets | MUST HAVE | Faker, Log generator | Gorle Sravani | Completed
S1 | S1 | US-004 | Ingest raw log files into Spark DataFrames | MUST HAVE | Log directory | Jillepalli Harshitha | Completed
S2 | S2 | US-005 | Parse log fields (timestamp, level, message, IP) | MUST HAVE | Regex, UDF | Naga Santhosh Nikhil | Completed
S2 | S2 | US-006 | Identify and classify error logs | MUST HAVE | Parsed logs | M Sandhiya | Completed
S2 | S2 | US-007 | Aggregate total logs and error counts | MUST HAVE | Spark SQL | Kompella Avanthi krishna Veni | Completed
S2 | S2 | US-008 | Analyze error frequency by time intervals | SHOULD HAVE | Timestamp data | Gorle Sravani | Completed
S3 | S3 | US-009 | Generate analytics reports in CSV format | MUST HAVE | Aggregated data | Kompella Avanthi krishna Veni | Completed
S3 | S3 | US-010 | Generate analytics reports in JSON format | MUST HAVE | Aggregated data | Jillepalli Harshitha | Completed
S3 | S3 | US-011 | Implement alert system for critical errors | MUST HAVE | Threshold logic | Amulya Thupakula | Completed
S3 | S3 | US-012 | Store alert history logs | SHOULD HAVE | File/DB | Naga Santhosh Nikhil | Completed
S4 | S4 | US-013 | Build interactive dashboard for log analytics | SHOULD HAVE | Streamlit | Jillepalli Harshitha | Completed
S4 | S4 | US-014 | Visualize error trends and top errors | SHOULD HAVE | Plotly | M Sandhiya | Completed
S4 | S4 | US-015 | Optimize Spark jobs and refactor code | COULD HAVE | Performance tuning | Gorle Sravani | Completed
S4 | S4 | US-016 | Final documentation and Agile report submission | MUST HAVE | Deliverables | Bhojanapalli Manikanta Rohit,Shruti Singh,Phanikumar Bathina,Kaif Qureshi,Divya Sree,Malini | Completed

## stand up meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Initial lack of clarity in Spark environment setup and project structure | Reviewed project objectives and finalized Spark setup approach
Sprint 1 | Day 5 | Issues while configuring local PySpark and dependencies | Installed compatible versions and verified SparkSession setup
Sprint 1 | Day 9 | Difficulty in handling different log formats during ingestion | Analyzed sample logs and defined a common ingestion strategy
Sprint 1 | Day 11 | Minor issues while converting raw logs into Spark DataFrames | Updated schema definitions and validated DataFrame structure
Sprint 2 | Day 14 | Challenges in accurately identifying and classifying error logs | Refined parsing logic and categorized errors based on severity
Sprint 2 | Day 18 | Aggregation queries were slow on larger log datasets | Optimized PySpark DataFrame operations and tested aggregations
Sprint 2 | Day 22 | Complexity in analyzing error trends over time intervals | Implemented time-based grouping and validated analytics results
Sprint 2 | Day 25 | Difficulty in aggregating metrics across multiple log attributes | Adjusted aggregation logic and verified output correctness
Sprint 3 | Day 29 | Unclear report structure for analytics output | Designed standardized report formats (CSV/JSON)
Sprint 3 | Day 33 | Issues while exporting analytics reports from Spark jobs | Debugged export logic and verified output files
Sprint 3 | Day 37 | Difficulty in defining alert thresholds for critical errors | Implemented configurable alert logic and tested sample cases
Sprint 3 | Day 41 | Alert history storage format needed improvement | Standardized alert logging and validated stored records
Sprint 4 | Day 45 | Initial challenges in designing Streamlit dashboard layout | Created basic UI structure and aligned components
Sprint 4 | Day 49 | Integration issues between PySpark outputs and Streamlit UI | Connected processed data to frontend and validated data flow
Sprint 4 | Day 53 | Performance lag during real-time dashboard updates | Optimized data loading and improved rendering logic
Sprint 4 | Day 55 | Minor UI inconsistencies in Streamlit dashboard | Refined layout and improved user interaction flow
Sprint 4 | Day 58 | Need for final testing and documentation before submission | Conducted end-to-end testing and completed project documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-01 | 2025-12-14 | Avanthi Krishna Veni, Jillepalli Harshitha, Priyadharshini, Phanikumar Bathina, Shruti Singh | Setting up PySpark environment and basic log ingestion. | Avoiding hard-coded file paths in PySpark scripts. | Continuing distributed log ingestion using PySpark. | Implemented PySpark scripts for log ingestion and initial parsing.
2 | Sprint 2 | 2025-12-15 | 2025-12-26 | Naga Santhosh Nikhil, Neeraj Vinod, Behara Sahithya, Ponnuru Asritha Sai, Divya Sree | Using regex-based parsing to structure logs into Spark DataFrames and extract error metrics. | Reducing overuse of RDDs when DataFrames and Spark SQL are more efficient. | Continuing distributed log ingestion using PySpark with modular parsing logic. | Implemented DataFrame-based log parsing, filtering, and initial error metrics generation.
3 | Sprint 3 | 2025-12-29 | 2026-01-09 | Gorle Sravani, Amulya Thupakula, Bhojanapalli Manikanta Rohit, Kaif Qureshi, Malini | Generating structured analytics reports in CSV/JSON format and implementing configurable alert logic for critical log events. | Avoiding manual report preparation and hard-coded alert thresholds. | Continuing DataFrame-based analytics processing and exporting results via PySpark. | Implemented automated analytics report generation and a configurable alert system for critical errors.
4 | Sprint 4 | 2026-01-12 | 2026-01-23 | Sandhiya, Karri Manikanta Sai, Mattaparthi Luhipriya, Annie Valentina | Developing an interactive dashboard to visualize log analytics and alerts. | Avoiding unoptimized Spark transformations and undocumented code changes. | Continuing end-to-end testing, performance optimization, and system refinement. | Developed an interactive log analytics dashboard and finalized system optimization and project documentation.